## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | USOnlineTestMGMT :001 | Design Documentation for Backend application | Sreenath | Suraj Pakhare | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | USOnlineTestMGMT :002 | Test Plan | Sreenath | Suraj Pakhare | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | USOnlineTestMGMT :003 | Bootstrapping the project | Sreenath | Suraj Pakhare | Simple | Low | RD:1 Application SetUp | RD: FlightDesinDocument_ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | USOnlineTestMGMT :004 | Entity Class and TableDEsign and Populating the data | Sreenath | Suraj Pakhare | Average | Low | RD2: Entity Class Design and RD3: Table Design | RD: OnlineTestMgmtDocument_ver2 | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | USOnlineTestMGMT :005 | Service Methods to add , delete , update ,and list all the user and their details. | Sreenath | Suraj Pakhare | Average | High | RD 4: Add,Delete,Update, Display all User. | RD: OnlineTestMgmtDocument_ver3 | Functional |  |  |  |  | 24 hrs
5 | 6 | Work session | High | USOnlineTestMGMT :006 | Service Methods to add , delete , update ,and list the user activities inside the workspace. | Sreenath | Suraj Pakhare | Average | High | RD7:Add,Delete, Update, Display all Entries in Workspace | RD: OnlineTestMgmtDocument_ver4 | Functional |  |  |  |  | 32hrs
6 | 7 | Work session | High | USOnlineTestMGMT :007 | Adding class level comments and methods level comments. | Sreenath | Suraj Pakhare | Easy | Low | RD8:Adding Comments & description | RD: OnlineTestMgmtDocument_ver5 | Functional |  |  |  |  | 1 hr
7 | 8
8 | 9
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | USOnlineTestMGMT :010 | Angular Project Documentation Designing | Sreenath | Suraj Pakhare | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional |  |  |  |  | 14hrs
| 17 | Standard document | High | USOnlineTestMGMT :011 | Test Plan | Sreenath | Suraj Pakhare | Average | Low |  |  | Non Functional |  |  |  |  | 16hrs
16 | 18 | Standard document | High | USOnlineTestMGMT :012 | Design Login And Singup Page General | Sreenath | Suraj Pakhare | Average | High |  |  | Functional |  |  |  |  | 12hrs
17 | 19 | Work session | High | USOnlineTestMGMT :013 | Desing navigation bar for both the User and Admin | Sreenath | Suraj Pakhare | Average | Low |  |  | Functional |  |  |  |  | 36hrs
18 | 20 | Work session | High | USOnlineTestMGMT :014 |  | Sreenath | Suraj Pakhare | Complex | Low | [7 empty] | 32hrs
19 | 21 | Work session | High | USOnlineTestMGMT :015 | Design Test Platform to Atttempt Test | Sreenath | Suraj Pakhare | Very Complex | High |  |  | Functional |  |  |  |  | 34hrs
20 | 22 | Work session | High | USOnlineTestMGMT :016 | Profile Page to Show attempt Test Result. | Sreenath | Suraj Pakhare | Average | Low |  |  | Functional |  |  |  |  | 36hrs
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USOnlineTestMGMT :010 | 1 | Wireframes and story boarding for each task | Suraj Pakhare
|  | 2 | Routing Url List | Danish Sharma
|  | 3 | Data classes details | Danish Sharma
|  | 4 | Angular service | Sachin Kumar
|  | 5 | Components details | Suraj Pakhare
| USOnlineTestMGMT :011 | 1 | Test Plan for Login | Suraj Pakhare
|  | 2 | Test plan for Signup | Suraj Pakhare
|  | 3 | Test Plan for Assign Test | Sachin Kumar
|  | 4 | Test plan for Show Test | Suraj Pakhare
|  | 5 | Test plan for checkScore | Suraj Pakhare
|  | 6 | Test Plan for Add And Show Question | Danish Sharma
|  | 7 | Test plan Delete & Update Question | Danish Sharma
| USOnlineTestMGMT :012 | 1 | Designing template Menu | Suraj Pakhare
|  | 2 | Adding Client Menu | Suraj Pakhare
|  | 3 | Adding Admin Menu | Suraj Pakhare
|  | 4 | Adding Question Component DropDown Menu | Danish Sharma
|  | 5 | Adding Test Componet DropDown Menu | Sachin Kumar
| USOnlineTestMGMT :013 | 1 | Design a form Login & SignUp | Suraj Pakhare
|  | 2 | Design client and admin pages | Suraj Pakhare
|  | 3 | Design Test Platform | Suraj Pakhare
|  | 4 | Design Profile Page to Show Attempted Test & Score | Suraj Pakhare
| USOnlineTestMGMT :014 | 1 | Design Add Test | Sachin Kumar
|  | 2 | Design View Tests | Sachin Kumar
|  | 3 | Design update Test & delete Test | Sachin Kumar
|  | 4 | Assign Test To user | Sachin Kumar
|  | 1 | Add Questions | Danish Sharma
|  | 2 | View Questions | Danish Sharma
|  | 3 | Update & Delete Questions | Danish Sharma
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USOnlineTestMGMT :001 | 1 | Entity Class Design | Danish Sharma |  | 4 hrs | 2 hrs | Completed | 3
|  | 2 | Table Design | Suraj Pakhare |  | 2 hrs | 2 hrs | Completed | 2
|  | 3 | Application Architecture | Suraj Pakhare |  | 1 hrs | 0.5 hrs | Completed | 1
|  | 4 | Use case diagram | Danish Sharma |  | 2 hrs | 0,5 hrs | completed | 2
|  | 5 | Sequence Diagram | Danish Sharma |  | 4 hrs | 0.5 hrs | Completed | 3
|  | 6 | Each use case detail description | Danish Sharma |  | 4 hrs | 0.5 hrs | Completed | 2.5
|  | 7 | Class Layer diagram | Sachin Kumar |  | 1 hrs | 0.5 hrs | Completed | 1
|  | 8 | Class Diagram | Danish Sharma |  | 2 hrs | 0.5 hrs | Completed | 2
|  | 9 | Webservice URL Details | Sachin Kumar |  | 2 hrs | 0.5 hrs | Completed | 2.5
2 | USOnlineTestMGMT :002 | 1 | Test plan for dao, | Everyone
|  | 2 | Test plan for service | Everyone
|  | 3 | Test plan for webservice methods | Everyone
3 | USOnlineTestMGMT :003 | 1 | Creating a Spring boot starter project | Everyone |  | 2 hrs | 0.5 hrs |  | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Everyone |  | 1 hrs | 0.5 hrs |  | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Everyone |  | 1 hrs | 0.5 hrs |  | 0.5 hrs
4 | USOnlineTestMGMT :004 | 1 | Entity Class Design | Suraj Pakhare
|  | 2 | Check tables are poulated in DB | Sachin Kumar
|  | 3 | Populate the Data | Sachin Kumar , SurajPakhare
5 | USOnlineTestMGMT :005 | 1 | Write all the services methods for Questions, Tests , User & Workspace Entity Classes | Sachin Kumar, Suraj Pakhare
|  | 2 | Written all the Dao Methods and implement the logic for fetching and adding data to database. | Sachin Kumar , SurajPakhare
|  | 3 | Written all the Exceptions for all the service & dao methods. | Sachin Kumar, Suraj Pakhare
|  | 4 | Written the Testcases for all the service and dao methods. | Sachin Kumar , SurajPakhare
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.